Applied Claude Code

Tier 2 Training Plan — Early Draft for Board Awareness

handlekraft  |  Target launch: Q2 2027

# A Note on the Status of This Document

This is an earlier-stage draft than the Tier 1 plan, shared for board awareness rather than decision. Tier 2 is deliberately less mature, for three reasons:

- It serves a different audience (mid-career knowledge workers retooling) who we will understand better after running one or two Tier 1 cohorts.

- The Claude Code and agentic development tooling landscape is moving quickly; locking a detailed curriculum a year in advance would be a mistake.

- The program will be co-developed and led by an experienced volunteer engineer we are still recruiting. Their perspective should shape the curriculum, not be imposed on after the fact.

What follows is a shape, not a finished plan. The intent is to describe the program clearly enough that the board can react to direction, scope, and audience — and so that we can recruit the right volunteer lead against a coherent brief.

# Program at a Glance

Name (working): Applied Claude Code

Length: 4 weeks, 16 hours per week (64 total contact hours)

Schedule: Evenings, online — consistent with Tier 1

Cost to learners: Free. Learners use their own laptop or request a loaner; all tools and infrastructure provided

Prerequisites: Completion of Tier 1 OR prior programming exposure, terminal comfort, and a real project the learner wants to build

Cohort size: 5–8 learners

Primary outcome: A graduate can build, ship, and support non-trivial software using Claude Code as their primary engineering partner — with the judgment to know when the AI is wrong

# Audience

Tier 2 serves two overlapping groups:

- Tier 1 graduates who have demonstrated aptitude and want to go deeper on the technical side. They bring product instincts and client communication skills; Tier 2 adds the depth to ship real software.

- Mid-career knowledge workers (analysts, operations leaders, technical managers, career changers with prior coding exposure) who want to retool substantively around agentic development rather than start from scratch.

The two groups learn well together. Tier 1 graduates bring product and client instincts the mid-career learners may lack; mid-career learners bring professional context and domain expertise the Tier 1 graduates may lack. The cohort is stronger for the mix.

# Guiding Philosophy

Applied Claude Code is not a coding bootcamp. It is a program for learning to ship software in a world where the AI can write the code. The core claim of the curriculum is that the valuable professional skill is no longer writing code line-by-line; it is directing, reviewing, integrating, and owning software that an AI agent largely writes.

Graduates finish the program having built and deployed real software that they own end to end. They understand the code well enough to debug it, extend it, and explain it — but their primary mode of work is to direct Claude Code and review its output critically.

# Learner Outcomes

By the end of the program, a graduate can do each of the following:

- Scope a software project realistically: what it will do, what it will not do, what a first working version looks like.

- Direct Claude Code to implement features in a real codebase, including navigating, reading, and making safe changes to existing code.

- Read and critically review AI-generated code — recognizing common failure modes, subtle bugs, and cases where the model is overconfident.

- Use version control (Git) fluently in a collaborative context: branching, pull requests, code review.

- Deploy and support a working application, including basic testing, monitoring, and incident response.

- Participate in professional software workflows: code review, documentation, handoffs, and written technical communication.

# Weekly Structure at a Glance

| Week | Theme | Core skill built | Artifact produced |
| --- | --- | --- | --- |
| 1 | The agentic mindset | Directing and reviewing Claude Code | Scoped project brief + first working feature |
| 2 | Working in real codebases | Navigation, safe change, version control | Reviewed pull request on a practice codebase |
| 3 | Shipping something real | Taking a project to a deployed state | Deployed application with meaningful functionality |
| 4 | Professional practice | Review, handoff, and handlekraft workflow | Documented project + portfolio package |

# Weekly Time Budget

Structure mirrors Tier 1: four evening sessions per week, four hours each, for 16 contact hours weekly. Kickoff on Monday, guided practice Tuesday, independent work with one-on-ones Wednesday, demo and retrospective Thursday. The consistency across tiers is intentional — it lowers cognitive load for learners who progress from Tier 1 and gives shared rhythm for instructors.

# Week 1 — The Agentic Mindset

## Intent

Most of this week is about breaking habits, not building them. Learners with prior coding exposure tend to reach for the keyboard; learners from Tier 1 tend to ask the AI for help with small pieces. Both patterns leave value on the table. The week trains a new default: start by briefing, reviewing, and iterating at the scope of a feature.

## Provisional sessions

- Session 1: The mental model. Demonstrations of Claude Code on real tasks; learners attempt their first directed feature in pairs.

- Session 2: Briefing well. How to write a task description the AI can act on. Practice with increasingly ambiguous requests.

- Session 3: Reading output critically. Common failure modes; when to accept, when to iterate, when to start over.

- Session 4: Scoping the project learners will carry through the program. Demo of each learner’s project brief and first feature.

# Week 2 — Working in Real Codebases

## Intent

Greenfield projects are easy compared to walking into an existing codebase. Most real professional work involves understanding what is there, making a small and safe change, and demonstrating through review that the change is correct.

## Provisional sessions

- Session 1: Navigating an unfamiliar codebase with AI assistance; mapping the structure before touching anything.

- Session 2: Version control depth: branches, pull requests, commit hygiene, resolving conflicts.

- Session 3: Code review — giving and receiving. Each learner reviews a peer’s change and receives a review on their own.

- Session 4: Practice codebase exercise: implement a small, real-feeling feature on a provided codebase with a full pull request and review cycle.

# Week 3 — Shipping Something Real

## Intent

The centerpiece week. Learners take the project scoped in Week 1 to a deployed, working state. The curriculum steps back; the instructor rotates for one-on-ones, unblocking issues and reviewing decisions.

## Provisional sessions

- Session 1: Deployment fundamentals — getting something real on the internet safely.

- Session 2: Building session with instructor rotation; mini-lessons on testing as patterns emerge.

- Session 3: Building session; focus on polish and handling the last mile.

- Session 4: Internal demo day. Each learner shows a working, deployed application with the story of one real problem they encountered and how they resolved it.

# Week 4 — Professional Practice

## Intent

Software that ships is not the same as software that can be maintained. This week turns the project into something a real organization could take over, and introduces the workflow handlekraft uses for its client delivery.

## Provisional sessions

- Session 1: Documentation that matters — what to write, what not to write.

- Session 2: Handoff and support: how to leave a project in a state where someone else can maintain it.

- Session 3: The handlekraft client workflow: intake, scoping, delivery, support.

- Session 4: Final demo day to an external audience, including a written one-page recommendation and a portfolio walkthrough.

# Open Questions for the Board (and for the Future Volunteer Lead)

These questions are deliberately unresolved. We want the volunteer lead to engage with them, and we want the board to weigh in on the scope:

- Is four weeks the right length, or should Tier 2 be six weeks like Tier 1? The case for four: the audience can move faster. The case for six: shipping real software takes time, and rushing it undermines the learning.

- Should the prerequisite be strict (prior coding plus terminal comfort) or open (anyone with Tier 1 completion or equivalent)? Stricter means a tighter, faster cohort; more open means a bigger pipeline but a harder class to teach.

- Should the Week 3 project be the learner’s own (higher motivation, variable scope) or a handlekraft client project (more consistent difficulty, tighter supervision)?

- What credential or portfolio artifact should Tier 2 graduates leave with? How does it differ from Tier 1?

- Who do we want as the volunteer lead? The person should be shipping production software with Claude Code or a comparable tool today — not last year.

# Post-Program Pathway

Portfolio and references. Graduates leave with a deployed application, a full pull request history, a written recommendation to a notional client, and a reference from the instructor.

handlekraft fellowship eligibility. Strong Tier 2 graduates are the priority pool for unpaid or paid fellowship roles on handlekraft client projects as those become available.

Mentorship track. Exceptional graduates are invited back to support future Tier 1 and Tier 2 cohorts, consistent with the “pay it forward” design of the overall handlekraft model.

# Resource Estimate

To be drafted jointly with the volunteer lead once they are identified. Expected to be somewhat lower than Tier 1 on a per-learner basis (shorter program, self-directed audience) but with a higher instructor-skill requirement.

# Status

This is an early draft shared for board awareness. The Tier 1 plan is the near-term decision the board is being asked to react to; Tier 2 is shared so the board has line-of-sight on the full program arc. Detailed Tier 2 design will be revisited after at least one Tier 1 cohort has run and once a volunteer lead has been identified.